## Frontend Bugs
Bug ID | Page / Module | Environment (Browser/Device) | Bug Category | Description | Steps to Reproduce | Expected Behavior | Actual Behavior | Severity | Status | Screenshot / Video Link | Date Reported | Due Date | Date of Fixing Bug | Assigned To | Fixed By
A-001 | Notifications Dropdown on Admin Portal (Header) | Chrome | Responsiveness | The minimum small screen size is 280 and the notifications dropdown is out of sight on that screen size. Its not responsive | update tailwind classes to make it responsive | must be visible within the screen size | partially visible | medium | Fixed | bugs\screenshots\notifications_dropdown.png | 1st Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
A-002 | Branch Management (All Branches Page) of Admin | Chrome | Responsiveness | The minimum small screen size is 280 and the Tables on Branch Management page are making this page irresponsive. Its not responsive | update tailwind classes to make it responsive | must be visible within the screen size | tables are making screen to scroll | medium | Fixed | bugs\screenshots\branch_management_page.png | 1st Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
A-003 | Branch Management (Side Bar Page) of Admin | Chrome | Responsiveness | The sidebar becomes short highted on 280 width and 500 height | update tailwind classes to make it responsive | hight of sidebar must be full | half heighted sidebar | medium | Fixed | bugs\screenshots\Branch Management Sidebar.png | 1st Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
A-004 | Branch Management (Side Bar Page) of Admin | Chrome | UI | The sidebar is showing both All Branches and Add Branch buttons as selected | update tailwind classes to solve this issue | only selected page must be hovered | both All Branches and Add Branch Buttons are hovered | medium | Fixed | bugs\screenshots\Branch Management Sidebar 2.png | 1st Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
A-005 | Branch Management (Add New Branch Page) of Admin | Chrome | Responsiveness | The form is making this page irresponsive | update tailwind classes to make it responsive | form must be within the screen | form is making the page irresponsive | medium | Fixed | bugs\screenshots\Branch Management Add New Branch.png | 1st Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
A-006 | Branch Management (Statistics Page) of Admin | Chrome | UI | The div after Revenue analytics heading must show the dates in centered alligned manner | update tailwind classes to solve this issue | must be center alligned | left alligned | medium | Fixed | bugs\screenshots\Branch Management Statistics.png | 1st Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
A-007 | Branch Management (Statistics Page) of Admin | Chrome | UI | The fontsize of the heading Branch Statistics & Revenue Analytics must be adjustable in accordance with the width | update tailwind classes to solve this issue | font size must be small for small screens | font size of heading Branch Statistics & Revenue Analytics is too much large | medium | Fixed | bugs\screenshots\Branch Management Statistics 2.png | 1st Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
A-008 | Notifications Dropdown on Admin Portal (Header) | Chrome | Logical | The notifications Dropdown in the admin header must call getSuspiciousActivities function instead of getTimeline function as you have defined in the adminApi.js the purpose of showing suspicious activities as notifications is to notify them about any suspicious activity if any happened not to notify them about all notifications in a specific timeline | in line number 46 of Notifications.jsx replace getTimeline with getSuspiciousActivities | notifications dropdown must show suspicious activities to the super admin | notifications dropdown is showing activity logs of a specific timeline which is wrong | high | Fixed | bugs\screenshots\notifications-suspicios-activities.png | 2nd Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
A-009 | All Admins Page | Chrome | Responsiveness | The numbers inside the 3 divs (above the Branch admins cards are getting outside those divs on small screens | update tailwind classes | on small screens make those 3 divs to be vertically aligned (one over another) instead of horizontal allignment | those 3 divs are horizontally alligned | medium | Fixed | bugs\screenshots\all-admins-page-icons.png | 2nd Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
A-010 | All Admins Page | Chrome | UI | The buttons on admins cards are justified to end. For smaller screens make them justify center or the best choice is justify between | update tailwind classes | justify between | justify end | low | Fixed | bugs\screenshots\admins-cards-buttons.png | 2nd Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
A-011 | Add New Admin Page | Chrome | UI | The font size of Add New Admin is too large on small screens | update tailwind classes | font size must be small for small screens | it’s a bit large | low | Fixed | bugs\screenshots\add-new-admin.png | 2nd Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
A-012 | Salespersons Page in Staff Management | Chrome | Responsiveness | This page is irresponsive may be because of form | update tailwind classes | it must be responsive | irresponsive | medium | Fixed | bugs\screenshots\Staff-Management-Salespersons-Page.png | 2nd Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
A-013 | SideBar on Salespersons Page in Staff Management | Chrome | Responsiveness | The sidebar on this page is irresponsive | update tailwindd classes | it must be responsive | irresponsive | medium | Fixed | bugs\screenshots\Staff-Management-SideBar-Salesperson.png | 2nd Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
A-014 | Staff Management Add New Salespersons Page | Chrome | UI | The font size of Add New Salesperson is too large on small screens | update tailwind classes | font size must be small for small screens | font size of heading Add New Salesperson is too much large | low | Fixed | bugs\screenshots\Add-new-Salesperson.png | 2nd Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
A-015 | Doctors Applications Page | Chrome | Responsiveness | The Doctors Applications Page is not Responsive | update tailwind classes | responsive | irresponsive | medium | Fixed | bugs\screenshots\Doctors-Applications.png | 2nd Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
A-016 | Task Management Page | Chrome | Responsiveness | This page is not responsive | update tailwindd classes | responsive | irresponsive | medium | Fixed | bugs\screenshots\task-management.png | 2nd Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
A-017 | Task Management Page | Chrome | UI | As per the requirements mentioned in the document we are required to show a proper task management board (like jira) | update the ui of this page and provide a board | tasks are shown in table | tasks must be shown in a board | high | Fixed | bugs\screenshots\tasks-table.png | 2nd Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
A-018 | Customer Management Page | Chrome | Responsiveness | The customer management page is irresponsive | update tailwindd classes | responsive | irresponsive | medium | Fixed | bugs\screenshots\Customer Management Page.png | 2nd Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
A-019 | Revenue Analytics Page | Chrome | Responsiveness | The revnue analytics page is not responsive | update tailwind classes | responsive | irresponsive | medium | Fixed | bugs\screenshots\revenue-analytics.png | 2nd Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
A-020 | Revenue Analytics Page | Chrome | UI | There is a div on revenue-analytics-page that is showing a loading card a circle in center and a rectangle at the top left | remove it | after loading it should be removed | its visible even after loading | medium | Fixed | bugs\screenshots\revenue-analytics-waste-card.png | 2nd Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
A-021 | User Engagement Page | Chrome | Responsiveness | This page is irresponsive | update tailwind classes | responsive | irresponsive | medium | Fixed | bugs\screenshots\User-Engagement-Page.png | 2nd Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
A-022 | Activity Logs Page | Chrome | Responsiveness | This page is irresponasive | update tailwind classes | responsive | irresponsive | medium | Fixed | bugs\screenshots\Activity Logs Page.png | 2nd Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
A-023 | Feedback and Complaints Analytics Page | Chrome | Responsiveness | This page is not responsive | update tailwind classes | responsive | irresponsive | medium | Fixed | bugs\screenshots\Feedback-Complaints-Analytics.png | 2nd Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
A-024 | Appointments Analytics Page | Chrome | Responsiveness | This page is not responsive | update tailwind classes | responsive | irresponsive | medium | Fixed | bugs\screenshots\Appointment-Analytics-Page.png | 2nd Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
A-025 | Admin Dashboard Footer | Chrome | UI | this is too much concise footer. Provide a professional footer | add some content in it | detailed footer | single line footer | medium | Fixed | bugs\screenshots\admin-Footer.png | 2nd Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
A-026 | Roles And Permissions Page | Chrome | Responsiveness | This page is not responsive | update tailwind classes | responsive | irresponsive | medium | Fixed | bugs\screenshots\Roles-Permissions-Admin.png | 2nd Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
A-027 | Notifications Page | Chrome | Responsiveness | This page is not responsive | update tailwindd classes | responsive | irresponsive | medium | Fixed | bugs\screenshots\Notifications-Page.png | 2nd Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
A-028 | Settings Page | Chrome | Responsiveness | The 2fa enable button on small screen is too bad because of irresponsiveness | update tailwindd classes | responsive | irresponsive | medium | Fixed | bugs\screenshots\Admin-Settings.png | 2nd Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
A-029 | Admin Dashboard Searchbar | Chrome | UX | the search bar must allow admin to search about any of the features which we are providing on dashboard. For example if admin searches about branches the search bar must show all the branch related activities that admin can do in a dropdown | implement this functionality on frontend | search bar must provide correct response on admins search | search bar is providing nothing | high | Fixed | bugs\screenshots\Search-Bar-Admin-Dashboard.png | 2nd Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
A-030 | Admin Landing Page | Chrome | Responsiveness | The Active Users and Response Time cards on Admin Setting image must not be visible on small screens | either remove them or make some change for maing it responsive | those 2 cards must be static beneath the setting image instead of floating on it | those 2 cards are floating on the setting image | medium | Fixed | bugs\screenshots\Landing-Page-Admin.png | 2nd Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
A-031 | Admin Landing Page | Chrome | Exagerated Lies | Stop presenting lies | remove ip whitelisting, automatic logout | correct info | incorrect info | high | Fixed | bugs\screenshots\landing-admin-details.png | 2nd Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
C-001 | Customer Doctor Landing Page | Chrome | UX | Though we have a single landing page for both customers and doctors it does not mean we are free to place any button anywhere. See how bad UX will be when a customer will see this login as doctor button. Just show a single login button on the top of the page at th very right top corner. and remove get started button from right top corner. further in hero section just show a get started button. remove login as doctor button. | update this landing page | as mentioned in description | current wrong state | medium | Fixed | bugs\screenshots\customer-doctor-landing.png | 2nd Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
C-002 | Customer Doctor Landing Page | Chrome | UX | Remove buttons in for doctors dection and make the heading for doctors more prominent | same as of description | just details | buttons are also shown | medium | Fixed | bugs\screenshots\doctors-landing.png | 2nd Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
C-003 | Customer Doctor Landing Page | Chrome | UX | Wrong date in footer | instead of hardcoding the date use Date object and get year from that object | current year | hard coded year | low | Fixed | bugs\screenshots\landing date.png | 2nd Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
C-004 | Customer Doctor Landing Page | Chrome | Responsiveness | philbox icons size is too large | update tailwindd classes | it must be responsive | irresponsive | medium | Fixed | bugs\screenshots\landing-doctor-foter-icon.png | 2nd Feb, 2026 | 5th Feb, 2026 |  | Muhammad Noman
C-005 | Customer Login Page | Chrome | UX | vite icon shows dev mode… update it to philbox's actual icon | Place philbox icon in place of vite icon | philbox icon on login page | vite icon | low | Fixed | bugs\screenshots\Customer Login Page | 20nd Feb, 2026 | 22nd Feb, 2026 |  | Muhammad Noman
C-006 | Notification drop down on customer dashboard | Chrome | Responsiveness | The minimum screen is 280 and the notification drop down goes out of sight | Make it visible and responsive | must be visible within the screen size | irresponsive | medium | Fixed | bugs\screenshots\customer-page-notification-dropdorn.PNG | 22nd Feb,2026 | 23rd Feb, 2026 |  | Muhammad Noman
C-007 | Customer Dashboard cards | Chrome | Responsiveness | The minimum screen is 280 and the cards icon goes out of cards. | Make it with within the cards | Must be adjusted according to the cards size. | irresponsive | medium | Fixed | bugs\screenshots\customer-Dasbboard-cards.PNG | 23rd Feb,2026 | 24th Feb, 2026 |  | Muhammad Noman
C-008 | Customer Medicine detail page | Chrome | Responsiveness | The minimum screen is 280 and the buy now and cadd to cart buttons and other things goes out of the card | Make it responsive | Must be adjusted according to the card size | irresponsive | medium | Fixed | bugs\screenshots\customer-medicine-details-page.PNG | 24th Feb,2026 | 25th Feb, 2026 |  | Muhammad Noman
C-009 | Customer order detail page | Chrome | Responsiveness | the minimum screen is 280 and the card size miss matched | make it responsive | Must be adjusted dso that in small screen all cards have same width | irresponsive | medium | Fixed | bugs\screenshots\Customer-order-detail-page.PNG | 23th Feb,2026 | 24th Feb, 2026 |  | Muhammad Noman
C-0010 | Customer Appointment page botton size | Chrome | Responsiveness | The buttons on the appointment cards are of unequal lengths make their width equal when the are in small screen | make them of equal width | Must be adjusted so that in small screen they seem to be of equal width | irresponsive | medium | Fixed | bugs\screenshots\customer-appointment-page-button size.PNG | 23th Feb,2026 | 24th Feb, 2026 |  | Muhammad Noman
C-0011 | Customer book Appointment cards and timeline | Chrome | Responsiveness | the min screen size is 280 and the cards of search bar and appointment width mismatched and the time line also goes out of sight | Make it visible and responsive | must be adjusted to equal widths also time line should be visible | irresponsive | medium | Fixed | bugs\screenshots\Customer-book-appointment responsiveness.PNG | 22nd Feb, 2026 | 23rd Feb, 2026 |  | Muhammad Noman
C-0012 | Customer Profile page security tab | Chrome | Responsiveness | the min screen size is 280 and the button goes out of the card | make it responsive | when the screen size is small the button should be inside the card | irresponsive | medium | Fixed | bugs\screenshots\customer-profile-security-tab.PNG | 22nd Feb, 2026 | 23rd Feb, 2026 |  | Muhammad Noman
D-001 | Doctor Registration page logo | Chrome | Ux | the logo of vite is shown instead of philbox logo | adjust the logo of philbox | must show the logo of philbox | vite icon | medium | Fixed | bugs\screenshots\doctor-registration-page.PNG | 22nd Feb, 2026 | 23rd Feb, 2026 |  | Muhammad Noman
D-002 | Doctor login page logo | Chrome | Ux | the logo of vite is shown instead of philbox logo | adjust the logo of philbox | must show the logo of philbox | vite icon | medium | Fixed | bugs\screenshots\doctor-registration-page.PNG | 22nd Feb, 2026 | 23rd Feb, 2026 |  | Muhammad Noman
D-003 | Doctor complete profile | Chrome | ux | the logo of vite is shown instead of philbox logo | adjust the logo of philbox | must show the logo of philbox | vite icon | medium | Fixed | bugs\screenshots\doctor-registration-page.PNG | 22nd Feb, 2026 | 23rd Feb, 2026 |  | Muhammad Noman
D-004 | Doctor Registration page logo | Chrome | Responsiveness | password and confirm password text bxes size mismatched | must be adjusted | the size of the textboxes must be responsive and well managed | irresponsive | medium | Fixed | bugs\screenshots\doctor-registration-page.PNG | 22nd Feb, 2026 | 23rd Feb, 2026 |  | Muhammad Noman

## Refactoring Log
Refactor ID | File(s) Affected | Reason for Refactoring | Before (Problem) | After (Solution) | Behavior Change (Yes/No) | Impact | Commit / PR | Date